## S2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Budget Tracking | 2.02 | Track Income & Expenses | Design UI for entering income and expense records | 2025-11-03 | 2025-11-08 | 100% | Sai Swaroop Manne
2 | 02. Budget Tracking | 2.02 | Track Income & Expenses | Develop backend API for storing income/expense entries | 2025-11-03 | 2025-11-08 | 100% | Sai Swaroop Manne
3 | 02. Budget Tracking | 2.02 | Track Income & Expenses | Implement validation for correct format and category inputs | 2025-11-03 | 2025-11-08 | 100% | Sai Swaroop Manne
4 | 02. Budget Tracking | 2.02 | Track Income & Expenses | Create budget category selection with dropdown defaults | 2025-11-03 | 2025-11-08 | 100% | Sai Swaroop Manne
5 | 02. Budget Tracking | 2.02 | Track Income & Expenses | Add chart visualization for income vs. expenses | 2025-11-03 | 2025-11-08 | 100% | Sai Swaroop Manne
6 | 02. Budget Tracking | 2.02 | Track Income & Expenses | Test integration of income/expense data with budget tracking | 2025-11-03 | 2025-11-08 | 100% | Sai Swaroop Manne
7 | 02. Budget Tracking | 2.02 | Track Income & Expenses | Perform Exploratory Testing on Track Income Functionality | 2025-11-03 | 2025-11-08 | 100% | Sai Swaroop Manne
8 | 02. Budget Tracking | 2.02 | Track Income & Expenses | Test field validation and DDV with QA scenarios | 2025-11-03 | 2025-11-08 | 100% | Sai Swaroop Manne
9 | 03. AI Advising & Finance | 3.01 | Get Financial Coaching | Develop AI model logic for personalized finance coaching | 2025-11-09 | 2025-11-14 | 100% | Sai Gnandeep Vangapandu
10 | 03. AI Advising & Finance | 3.01 | Get Financial Coaching | Integrate frontend chatbot interface for coaching Q&A | 2025-11-09 | 2025-11-14 | 100% | Sai Gnandeep Vangapandu
11 | 03. AI Advising & Finance | 3.01 | Get Financial Coaching | Enable suggestion system using income/expense history | 2025-11-09 | 2025-11-14 | 100% | Sai Gnandeep Vangapandu
12 | 03. AI Advising & Finance | 3.01 | Get Financial Coaching | Build feedback capture mechanism for coaching improvement | 2025-11-09 | 2025-11-14 | 100% | Sai Gnandeep Vangapandu
13 | 03. AI Advising & Finance | 3.01 | Get Financial Coaching | Test coaching recommendations using test data | 2025-11-09 | 2025-11-14 | 100% | Sai Gnandeep Vangapandu
14 | 03. AI Advising & Finance | 3.01 | Get Financial Coaching | Test concurrency by simulating multiple users | 2025-11-09 | 2025-11-14 | 100% | Sai Gnandeep Vangapandu
15 | 03. AI Advising & Finance | 3.01 | Get Financial Coaching | Perform Exploratory Testing on financial coaching Functionality | 2025-11-09 | 2025-11-14 | 100% | Sai Gnandeep Vangapandu
16 | 03. AI Advising & Finance | 3.01 | Get Financial Coaching | Verify data connectivity for AI models and user inputs | 2025-11-09 | 2025-11-14 | 100% | Sai Gnandeep Vangapandu
17 | 03. AI Advising & Finance | 3.03 | Learn Financial Literacy | Design lesson module for basic financial concepts | 2025-11-15 | 2025-11-18 | 100% | Kavya Sri Myakala
18 | 03. AI Advising & Finance | 3.03 | Learn Financial Literacy | Create backend for loading quiz and lesson content | 2025-11-15 | 2025-11-18 | 100% | Kavya Sri Myakala
19 | 03. AI Advising & Finance | 3.03 | Learn Financial Literacy | Develop scoring and progress tracking features | 2025-11-15 | 2025-11-18 | 100% | Kavya Sri Myakala
20 | 03. AI Advising & Finance | 3.03 | Learn Financial Literacy | Enable media content embedding (e.g., video/audio lessons) | 2025-11-15 | 2025-11-18 | 100% | Kavya Sri Myakala
21 | 03. AI Advising & Finance | 3.03 | Learn Financial Literacy | Ensure crosscut: Connectivity to external resources | 2025-11-15 | 2025-11-18 | 100% | Kavya Sri Myakala
22 | 03. AI Advising & Finance | 3.03 | Learn Financial Literacy | Test field validation on quiz inputs | 2025-11-15 | 2025-11-18 | 100% | Kavya Sri Myakala
23 | 03. AI Advising & Finance | 3.03 | Learn Financial Literacy | Test lesson progress retention and default settings | 2025-11-15 | 2025-11-18 | 100% | Kavya Sri Myakala
24 | 03. AI Advising & Finance | 3.03 | Learn Financial Literacy | Perform Exploratory Testing on the financial literacy functionality | 2025-11-15 | 2025-11-18 | 100% | Kavya Sri Myakala

## S3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 02. Budget Tracking | 2.03 | Trace Currency | Implement third-party API integration for fetching real-time exchange rates (USD to INR, CNY, etc.). | Y | 2025-11-18 | 2015-11-21 | 100% | Sai Swaroop Manne
2 | 02. Budget Tracking | 2.03 | Trace Currency | Design and integrate the UI component to display converted amounts on the expense details page. | Y | 2025-11-18 | 2015-11-21 | 100% | Sai Swaroop Manne
3 | 02. Budget Tracking | 2.03 | Trace Currency | Implement Data Validation logic to ensure conversion is blocked or flagged if external FX data is stale or unavailable. | Y | 2025-11-18 | 2015-11-21 | 100% | Sai Swaroop Manne
4 | 02. Budget Tracking | 2.03 | Trace Currency | Perform Exploratory Testing on Trace Currency Functionality | N | 2025-11-18 | 2015-11-21 | 50% | Sai Swaroop Manne
5 | 03. AI Advising & Financial Literacy | 3.04 | Monitor Engagement | Define and implement backend logic to log all user events (views, clicks) on financial literacy articles. | Y | 2025-11-22 | 2025-11-24 | 100% | Sai Swaroop Manne
6 | 03. AI Advising & Financial Literacy | 3.04 | Monitor Engagement | Build an internal reporting endpoint to calculate and aggregate engagement metrics. | Y | 2025-11-22 | 2025-11-24 | 100% | Sai Swaroop Manne
7 | 03. AI Advising & Financial Literacy | 3.04 | Monitor Engagement | Implement Internal Entitlement checks to ensure only Marketing/Data Analyst roles can access the engagement reports. | Y | 2025-11-22 | 2025-11-24 | 100% | Sai Swaroop Manne
8 | 03. AI Advising & Financial Literacy | 3.04 | Monitor Engagement | Perform Exploratory Testing on Monitor Engagement Functionality | N | 2025-11-22 | 2025-11-24 | 50% | Sai Swaroop Manne
9 | 04. Tax & Compliance | 4.01 | Handle Resources | Set up a secure, restricted cloud storage repository for internal and external tax resources. | Y | 2025-11-25 | 2025-11-29 | 100% | Sai Swaroop Manne
10 | 04. Tax & Compliance | 4.01 | Handle Resources | Build the user interface for F-1 students to search and view public tax/compliance guides. | Y | 2025-11-25 | 2025-11-29 | 100% | Sai Swaroop Manne
11 | 04. Tax & Compliance | 4.01 | Handle Resources | Implement Internal Security Checks to ensure non-authorized roles cannot download restricted tax resources. | Y | 2025-11-25 | 2025-11-29 | 100% | Sai Gnandeep Vangapandu
12 | 04. Tax & Compliance | 4.01 | Handle Resources | Perform Exploratory Testing on Handle Resources Functionality | N | 2025-11-25 | 2025-11-29 | 50% | Sai Gnandeep Vangapandu
13 | 04. Tax & Compliance | 4.03 | Update Policies | Design and implement the Admin interface for Compliance Officers to edit/upload privacy and data retention policies. | Y | 2025-11-30 | 2025-12-02 | 100% | Sai Gnandeep Vangapandu
14 | 04. Tax & Compliance | 4.03 | Update Policies | Implement Field Validation on all policy text input fields (e.g., character limits, special character checks). | Y | 2025-11-30 | 2025-12-02 | 100% | Sai Gnandeep Vangapandu
15 | 04. Tax & Compliance | 4.03 | Update Policies | Implement Internal Entitlement checks to ensure only Legal Specialist/Compliance Analyst roles can modify policies. | Y | 2025-11-30 | 2025-12-02 | 100% | Sai Gnandeep Vangapandu
16 | 04. Tax & Compliance | 4.03 | Update Policies | Perform Exploratory Testing on Update Policies Functionality | N | 2025-11-30 | 2025-12-02 | 50% | Sai Gnandeep Vangapandu
18 | 04. Tax & Compliance | 4.04 | Manage Reports | Define data sources and logic for generating the Tax Year Summary Report (Income, Residency Days, Deductions). | Y | 2025-12-03 | 2025-12-07 | 100% | Sai Gnandeep Vangapandu
19 | 04. Tax & Compliance | 4.04 | Manage Reports | Build the Report Generation Service endpoint to process data and output the summary report as a CSV/PDF file. | Y | 2025-12-03 | 2025-12-07 | 100% | Sai Gnandeep Vangapandu
20 | 04. Tax & Compliance | 4.04 | Manage Reports | Perform Exploratory Testing on Manage Reports Functionality | N | 2025-12-03 | 2025-12-07 | 50% | Sai Gnandeep Vangapandu
21 | 05. Support & Operations | 5.01 | Monitor Subscriptions | Integrate with the payment gateway API to pull and synchronize user subscription status data. | Y | 2025-12-08 | 2025-12-10 | 100% | Sai Gnandeep Vangapandu
22 | 05. Support & Operations | 5.01 | Monitor Subscriptions | Create the internal dashboard view to display subscription monitoring metrics (MRR, Churn Rate). | Y | 2025-12-08 | 2025-12-10 | 100% | Kavya Sri Myakala
23 | 05. Support & Operations | 5.01 | Monitor Subscriptions | Implement Internal Access Control to ensure only Finance/Compliance can view billing data on the dashboard. | Y | 2025-12-08 | 2025-12-10 | 100% | Kavya Sri Myakala
24 | 05. Support & Operations | 5.01 | Monitor Subscriptions | Perform Exploratory Testing on Monitor Subscriptions Functionality | N | 2025-12-08 | 2025-12-10 | 50% | Kavya Sri Myakala
25 | 05. Support & Operations | 5.02 | Manage Payment | Implement the secure API endpoints for payment processing and discount/promo code validation logic. | Y | 2025-12-11 | 2025-12-14 | 100% | Kavya Sri Myakala
26 | 05. Support & Operations | 5.02 | Manage Payment | Build the internal 'Refund Tool' interface and corresponding backend logic. | Y | 2025-12-11 | 2025-12-14 | 100% | Kavya Sri Myakala
27 | 05. Support & Operations | 5.02 | Manage Payment | Implement Internal Role Checks on the Refund Tool to ensure only Accountant/Admin roles can initiate a refund. | Y | 2025-12-11 | 2025-12-14 | 100% | Kavya Sri Myakala
28 | 05. Support & Operations | 5.02 | Manage Payment | Perform Exploratory Testing on Manage Payment Functionality | N | 2025-12-11 | 2025-12-14 | 50% | Kavya Sri Myakala
29 | 05. Support & Operations | 5.03 | Handle Users' Request | Integrate a Customer Support ticketing system (e.g., Zendesk) to create and log user requests. | Y | 2025-12-15 | 2025-12-16 | 100% | Kavya Sri Myakala
30 | 05. Support & Operations | 5.03 | Handle Users' Request | Design and implement the 'Agent View' dashboard for support staff to see ticket queues and user history snippets. | Y | 2025-12-15 | 2025-12-16 | 100% | Kavya Sri Myakala
31 | 05. Support & Operations | 5.03 | Handle Users' Request | Implement External Restriction to ensure a student can only query the status of their own support tickets. | Y | 2025-12-15 | 2025-12-16 | 100% | Kavya Sri Myakala
32 | 05. Support & Operations | 5.03 | Handle Users' Request | Perform Exploratory Testing on Handle Users' Request Functionality | N | 2025-12-15 | 2025-12-16 | 50% | Kavya Sri Myakala