## Road Map
F1NANCE
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/28/2025 | SPRINT2 - 11/18/2025 | SPRINT3 - 12/16/2025
01. Account Management | 01.01 Create Account | 3 | X
| 01.02 Modify Account | 3 | X
| 01.03 View Account Information | 2 | X
| 01.04 Upload Documents | 4 | X |  |  | Sprint 1 (10/07/2025 - 10/28/2025)
02. Budget Tracking | 02.01 Manage Bank Accounts | 4 | X |  |  | Planned S2 (10/29/2025 - 11/18/2025) | Actual S2 (10/29/2025 - 11/18/2025)
| 02.02 Track Income & Expenses | 5 |  | X |  | Planned S3 (11/19/2025 - 12/16/2025) | Actual S3 (11/19/2025 - 12/16/2025)
| 02.03 Trace Currency | 3 |  |  | X
03. AI Advising & Financial Literacy | 03.01 Get Financial Coaching | 5 |  | X
| 03.02 Receive Notifications | 3 |  | X
| 03.03 Learn Financial Literacy | 3 |  | X
| 03.04 Monitor Engagement | 2 |  |  | X
04. Tax & Compliance | 04.01 Handle Resources | 4 |  |  | X
| 04.02 Manage Tax Guides | 3 |  | X
| 04.03 Update Policies | 3 |  |  | X
| 04.04 Manage Reports | 4 |  |  | X
05. Support & Operations | 05.01 Monitor Subscriptions | 2 |  |  | X
| 05.02 Manage Payment | 3 |  |  | X
| 05.03 Handle Users' Request | 2 |  |  | X
|  | VELOCITY: | 16 | 19 | 23