## Team 2 - Report
Team 2: Jenkins Implementation Planning and Progress Tracking
Admin: | Vinh Long Tran
Sprint | Task Title | Description | Progress
PREP | Download and Install Java JDK and Jenkins | • Install Java JDK • Install Jenkins | 100%
PREP | Jenkins Configuration | • Install required plugins: • Pipeline Plugin • Git Plugin • GitHub Integration plugin • Create Admin User • Configure global security • Manage and Assign Roles | 100%
PREP | AWS Jenkins Setup | • Create two EC2 Instances: Dev, and QA • Create Key-Pair • Launch Instances | 100%
PREP | Basic Integration on dev and qa server | • Install Git on both server • Install Docker on Jenkins server • Install Nginx on Jenkins server • Install NodeJS on Jenkins server | 100%
PREP | Initial Pipeline Setup | • Create a basic Jenkins pipeline job • Develop a simple Jenkinsfile for frontend and backend applications • Execute the pipeline on the Dev EC2 instance | 100%
S1 | Install and Configure Additional Plugins | • Install Blue Ocean, Jira, and Pipeline Utility Steps plugins to improve UI, enable Jira tracking, and enhance scripting. • Configure authentication & API access for smooth integration with Slack and Jira. | 100%
S1 | Slack Notification Enhancements | • Configure Slack Plugin with clear, detailed messages (user stories, env, stagging/production). | 100%
S1 | Deployment Notifications | • Modify Jenkins pipeline to trigger Slack notifications on deployment success/failure. | 100%
S1 | Pipeline Optimization & Cleanup | • Optimize Dev/QA pipelines for faster build times. • Enable automated workspace cleanup post-build to save storage. | 100%
S1 | Staging & Target Environments | • Create separate pipelines for Staging and Target (DEV, QA) with clear notification flows. | 100%
S2 | Enable tasks/pipeline automation | We plan to configure Jenkins to automate build, test, and deployment tasks through a declarative Jenkinsfile. This includes defining multiple stages (checkout, build, test, deploy) and each commit or pull request now triggers the pipeline automatically. | 100%
S2 | Jenkins Plugin Configuration | Install required plugins: • Blue Ocean Plugin • Timestamper | 100%
S2 | Automatically trigger deployment pipelines once code change has been done on git. | We set up a GitHub webhook that triggers Jenkins pipelines whenever code changes are pushed to the repository. | 100%
S2 | Initial challenges in automating deployments and sending Jenkins alerts. | • Credential issues connecting to Github, Slack, Docker, EC2 • Old Dockers images are hard to clean up to make room for deploying new image • Security issues when connecting to database | 100%
S2 | Recognized the need for comprehensive monitoring and logging | Build numbers are appropriately marked and monitored vigorously | 100%
S2 | Manage Jenkins plugins carefully and keep them up to date to benefit from new features and bug fixes | • Git Plugins • Git Integration Plugin | 100%
S2 | Regularly update Jenkins and its plugins to patch security vulnerabilities | Periodically monitor the pipeline and its building process. Stay up to date with any new updates of any plugins. | 100%
S3 | Implement Role-Based Access Control (RBAC) | We plan to configure the Role-Based Authorization Strategy plugin to define permission levels for admin, developer, and viewer roles, improving access control and security within Jenkins. | 100%
S3 | Integrate ESLint with Warnings Next Generation Plugin (updated from SonarQube) | We will integrate ESLint for static code analysis in place of SonarQube. The Warnings Next Generation plugin will be used to display ESLint issues directly in Jenkins UI to ensure front-end code quality and maintainability. | 100%
S3 | Set Up OWASP Dependency-Check | As part of securing our CI pipeline, we will configure the OWASP Dependency-Check plugin to scan third-party libraries for known vulnerabilities and generate alerts during build time | 100%
S3 | Add Manual Approval for Production Deployment | We plan to introduce a manual approval gate using the Promoted Builds plugin or Jenkins input step before deploying to QA. This allows us to verify readiness and prevents accidental releases. | 100%
S3 | Integrate JMeter for Performance Testing | JMeter scripts will be added to evaluate API performance. Test results will be visualized in Jenkins post-build to ensure application responsiveness and catch regressions early. | 100%
S3 | Retry Failed Stages Automatically | To make the pipeline more resilient, we plan to implement retry logic for unstable steps like Docker login or ECR push to reduce build failures caused by temporary issues. | 100%
S3 | Publish Test and Coverage Reports | We will configure Jenkins to collect and display JUnit test results and code coverage reports, allowing the team to quickly verify the quality and reliability of each build. | 100%
S3 | Integrate Jenkins with Grafana via Prometheus | We plan to expose Jenkins job metrics using the Prometheus plugin and visualize real-time build stats, trends, and failure rates using Grafana dashboards. | 100%